## Instructions
Project Name | New E-Commerce
Module Name | Product Page
Created By | Satyam Mishra
Created Date | 2024-09-13
Peer Review By | Super AGI
Peer Reviewed Date
|  | Link of the Product Page : | https://www.flipkart.com/mivi-duopods-k4-tws-rich-bass-50h-playtime-ai-enc-low-latency-type-c-5-3-bt-earbuds-bluetooth-gaming/p/itm377fc213a2bc4?pid=ACCGPYGHRCW7TFJG&lid=LSTACCGPYGHRCW7TFJGU7S436&marketplace=FLIPKART&store=0pm%2Ffcn&srno=b_1_1&otracker=browse&fm=organic&iid=en_4CqSf48BmzQPo0K90idlJvTp6No6Vv9c9aFyLk9hQQaQG90PbA0FJiiilqKr2BBT3c5WL8bNepCC3FtoiSO0T_UFjCTyOHoHZs-Z5_PS_w0%3D&ppt=browse&ppn=browse&ssid=gzw084gwwg0000001725959920452
* Refer for Test Case
Scenario TID | Testing Type
FT001 | Functional Testing - Platform/Content Testing
UI001 | UI/UX Testing
ET001 | Exploratory Testing
RT001 | Regression Testing
API001 | API Testing
PT001 | Performance Testing
CB001 | Cross Browser Testing

## Test Plan
Test Plan for New E-Commerce Product Page
Testing Objectives
The objective of this test plan is to verify that the newly developed e-commerce product page functions smoothly, is user-friendly, secure, performs efficiently, and is ready for launch. It ensures that the page displays correct product information and provides a seamless shopping experience without any major issues at go-live.
Verify Functionality: Ensure that all functionalities of the product page (navigation, product details, add to cart, buy now, etc.) operate correctly.
Validate UI/UX: Confirm that the user interface is intuitive, consistent, and responsive across different devices and browsers.
Ensure Performance: Test page load times and responsiveness under various conditions.
Check Security: Validate that sensitive information is protected, and the application is secure against common vulnerabilities.
Confirm Integration: Ensure smooth integration with external systems (APIs, database etc.).
Access Information
Test Environment Access: URL to access the test environment, login credentials, and any other required access details will be provided separately.
Test Data: Predefined product information, user accounts, and test payment methods will be shared.
Testing Environment
Configurations Matrix:
Browser/Device | OS | Version | Screen Resolution | Network Speed | Mobile | Desktop
Chrome | Windows 10/11, macOS | Latest | 1920x1080, 1366x768 | 3G, 4G, Broadband | Yes | Yes
Firefox | Windows 10/11, macOS | Latest | 1920x1080, 1366x768 | 3G, 4G, Broadband | Yes | Yes
Safari | iOS, macOS | Latest | iPhone 12, iPad | 3G, 4G, Wi-Fi | Yes | No
Edge | Windows 10/11 | Latest | 1920x1080 | Broadband | No | Yes
Test Servers/Environment:
QA Environment URL: [URL for staging environment]
Production Environment URL: [URL for live environment]
API Test Environment: [API end-points for dev/test]
Selenium Grid:
Hub URL: [Selenium Grid Hub URL]
Node Configurations: Browser and OS configurations for grid nodes
Tools
Selenium Grid: For cross-browser testing across different devices and browser versions.
Zephyr: For test management, test case creation, execution, and tracking.
Selenium: For functional automation testing.
Postman and RestAssured: For API testing.
Appium: For mobile app testing.
TestNG: For test execution and reporting.
GitLab, Jenkins: For version control, CI/CD, and collaboration.
Jira: For defect tracking.
JMeter: For performance/load testing.
Google Sheets/Excel: For test case management and reporting.
Testing Scopes
Functional Testing: Using Selenium and TestNG for web functionality.
UI/UX Testing: Manual and automated tests for user interface.
API Testing: Using Rest Assured and Postman to validate APIs.
Mobile Testing: Using Appium for mobile app testing.
Performance Testing: Using JMeter for load testing.
Security Testing: Vulnerability assessments.
Cross-Browser Testing: Using Selenium Grid for compatibility testing.
Inclusions
Product Page Features:
Product Listing: Ensure product are displayed with accurate details, images, and descriptions.
Compare and Filtering: Validate that comparing by price, name, ratings, and filtering by attributes like color work correctly.
Product Details: Confirm that product images, videos, and variants are properly displayed.
Cart Functionality: Test adding products to the cart, updating quantities, and removing items.
Buy Now Process: Ensure the buy now process works for both guest and registered users.
Offers and Coupons: Test the application of valid/invalid coupons and discount offers.
User Management: Verify registration, profile editing, and address management.
Pricing and Discount Offers
Interactive Elements: (Buttons, Links, etc.)
Customer Reviews and Ratings
Shipping and delivery information
Warranty and return policies
UI Elements:
Display Settings: Ensure text fonts, images, and videos are correctly displayed and formatted.
Cross-Reference Links: Check internal and external URLs for correctness and accessibility.
Performance Testing:
Load Times: Measure how quickly the page loads and responds to user interactions under different conditions.
Security Testing:
Data Protection: Verify encryption and secure handling of user data.
Compatibility Testing:
Browser Compatibility
Device Compatibility
Usability Testing:
Page Navigation
User Interface Consistency
Accessibility Features
CI/CD Integration:
To automate the process of test execution, reporting, and deployment through CI/CD pipelines to ensure continuous integration and continuous delivery of the e-commerce product page. This approach helps in running tests automatically, catching issues early, and deploying bug-free code efficiently, We need to automate test cases executed with Selenium and TestNG triggered through GitLab CI/CD pipeline after each commit.
Exclusions
Backend database and server-side functionality (unless explicitly part of the scope)
Defect Reporting Procedure
Identification: Report defects identified during testing with detailed descriptions, screenshots, and steps to reproduce.
Logging: Use Jira for logging defects, classifying them into categories such as Critical, Major, Minor, or Trivial.
Tracking: Monitor the status of defects through Jira, ensuring timely resolution and retesting.
Resolution: Assign defects to developers, retest once fixed, and verify that the issue is resolved.
Testing Instructions
Functional Testing - Exploratory Testing:
Product Categories: Browse through categories to check navigation, product listings, and search functionality.
Product Details Page: Validate the images gallery, zoom functionality, video embeds, and variant options.
Cart Functionality: Test adding multiple items, updating quantities, and deleting items from the cart.
Checkout Process: Validate guest and registered checkouts, including payment methods and order confirmation.
Offers and Coupons: Test valid and invalid coupons and check the application of discounts.
User Registration and Management: Verify sign-up, profile editing, and address management.
API Testing:
Rest Assured: Test API endpoints for retrieving product data, cart operations, and checkout processes.
Mobile Testing:
Appium: Verify the functionality and responsiveness of the mobile version of the product page.
UI/UX Testing:
Display Settings: Validate text fonts, image placement, and video playback.
Cross-Reference Links: Ensure all internal and external URLs are functional and correct.
Usability Testing
Evaluate the overall user experience by observing how real users interact with the product page.
Data Validation Testing
Ensure the accuracy and correctness of data displayed on the product page.
Integration Testing
Validate how well the product page integrates with other systems (e.g., backend, third-party APIs).
Regression Testing
Ensure that new updates or code changes do not introduce defects into previously working functionalities.
Performance Testing:
Load Testing: Use JMeter to simulate high traffic and measure the page’s response.
Security Testing:
Data Protection: Conduct vulnerability scans and assess the security of data handling.
Cross-Browser Testing:
Selenium Grid: Execute test cases across different browsers and devices to ensure compatibility.
Test Schedule
Day | Task
Day 1 | Set up the test environment, configure Selenium Grid and GitLab CI/CD pipeline.
Day 2 | Prepare test data and finalize test cases in Zephyr and TestNG.
Day 3 | Execute functional and UI/UX testing using Selenium and TestNG.
Day 4 | Perform API testing with Rest Assured and mobile testing with Appium.
Day 5 | Conduct performance testing with JMeter.
Day 6 | Execute security testing and verify all integrations.
Day 7 | Final regression testing, address any issues, and prepare for go-live.
Test Deliverables
Test Plan: Detailed document outlining the testing objectives, scope, strategy, and schedule.
Test Cases: Documented test cases in Zephyr, executed using TestNG.
Defect Reports: Logged in Jira with status updates and resolution details.
Test Execution Report: Summary of test execution results, including passed/failed cases.
Go-Live Sign-Off: Final approval for production deployment.
Entry and Exit Criteria
Entry Criteria:
Test Environment: Configured and accessible.
Test Data: Prepared and accurate.
Test Cases: Finalized in Zephyr.
Selenium Grid: Set up and operational.
Rest Assured: API endpoints ready for testing.
Appium: Mobile app configurations complete.
Exit Criteria:
Defects: All critical and major defects resolved.
Testing Completion: All planned tests executed and documented.
Approval: Stakeholders approve the test results and go-live readiness.
Test Execution
Entry Criteria:
Test Environment: Fully configured and accessible.
Test Data: Available and accurate.
Test Cases: Finalized in Zephyr.
Tools: Selenium, Rest Assured, Appium, TestNG, GitLab CI/CD configured.
Exit Criteria:
Execution Completion: All test cases executed, and defects reported.
Validation: Critical functionalities validated, performance metrics within acceptable limits.
Test Closure
Entry Criteria:
Testing: All cases executed, critical issues resolved.
Defects: Addressed and retested.
Exit Criteria:
Reports: Final test execution report completed.
Approval: Final go-live sign-off from stakeholders.
Documentation: All test artifacts documented and stored.
Bug Logging Procedure
Defect Identification: Report issues with detailed steps and screenshots.
Logging: Use Jira to log defects, including severity and description.
Tracking: Monitor status and progress of defect resolution.
Verification: Retest fixed defects to confirm resolution.
Risks and Mitigations
Risk | Mitigation
Short testing window | Prioritize testing, focus on critical functionalities, and use automation.
Integration Issues | Thoroughly test integrations and have contingency plans.
High Traffic Load | Perform load testing and optimize performance.
Cross-Browser Compatibility Issues | Use Selenium Grid for extensive cross-browser testing.
Security Vulnerabilities | Conduct comprehensive security audits and address vulnerabilities.
Approvals
Test Lead: [Name], [Signature], [Date]
QA Manager: [Name], [Signature], [Date]
Project Manager: [Name], [Signature], [Date]
Stakeholders: [Names], [Signatures], [Dates]

## Test Cases
Scenario TID | Test Scenario | Test Case ID | Test Data | Test Case Title | Pre Condition | Steps to Execute | Expected Result | Actual Result | Status | Executed QA Name | Misc (Comments) | Priority | Is Automated
FT001 | Product Title Display | TC001 | N/A | Verify Product Title Display | User is on the product page | 1. Open product page 2. Check the product title displayed. | Product title should be correctly displayed on the product page. | N/A | Pass | QA Name | Product title must match the actual product being displayed. | High | Yes
FT002 | Product Image Gallery | TC002 | N/A | Validate Image Gallery Functionality | User is on the product page | 1. Open product page 2. Switch between images in the gallery. | Images should switch smoothly, and the gallery should load without errors. | N/A | Pass | QA Name | Test image transitions and loading time. | High | Yes
FT003 | Image Zoom Functionality | TC003 | N/A | Test Image Zoom Functionality | User is on the product page | 1. Hover over the product image 2. Verify zoom functionality. | Image zoom feature should work, allowing closer inspection of the product image. | N/A | Pass | QA Name | Verify zoom responsiveness. | Medium | Yes
FT004 | Product Variants Selection | TC004 | Variants (Size, Color, etc.) | Verify Product Variant Selection | User is on the product page | 1. Open product page 2. Select different product variants (size, color). | The selected variant should be reflected correctly on the product page (image, price, stock). | N/A | Pass | QA Name | Check for variant-related UI issues. | High | Yes
FT005 | Product Price Display | TC005 | Discounted price, Offers | Verify Product Price Display | User is on the product page | 1. Open product page 2. Check if the product price, including discounts, is displayed correctly. | The product price and discounts should be displayed accurately and updated as per the selected variant. | N/A | Pass | QA Name | Check different offers if applicable. | High | Yes
FT006 | Product Availability Check | TC006 | Location (Pincode) | Verify Product Availability | User is on the product page | 1. Open product page 2. Enter a pincode to check product availability. | Product availability status should be correctly updated as per the pincode. | N/A | Pass | QA Name | Verify availability per location. | Medium | Yes
FT007 | Add to Cart Functionality | TC007 | Product Variants (Qty, Size) | Validate Add to Cart Functionality | User is on the product page | 1. Open product page 2. Select variant and click "Add to Cart" button 3. Verify cart updates. | Product should be successfully added to the cart with the correct quantity and variant. | N/A | Pass | QA Name | Test multiple items and updates. | High | Yes
FT008 | Product Description Validation | TC008 | N/A | Verify Product Description | User is on the product page | 1. Open product page 2. Scroll to product description section 3. Validate content. | Product description should be complete and contain all relevant details (features, specs, etc.). | N/A | Pass | QA Name | Ensure content formatting is correct. | Medium | Yes
FT009 | Review and Rating Display | TC009 | N/A | Validate User Reviews and Ratings Display | User is on the product page | 1. Open product page 2. Scroll to reviews section 3. Verify customer reviews and ratings. | Customer reviews and ratings should load correctly, displaying the latest feedback. | N/A | Pass | QA Name | Verify review sorting functionality. | Medium | Yes
FT010 | Add Review Functionality | TC010 | User Login Data | Validate Add Review Function | User is logged in and on the product page | 1. Open product page 2. Scroll to reviews section 3. Add a new review and submit it. | The review should be successfully submitted and displayed under the customer review section. | N/A | Pass | QA Name | Ensure character limits are respected. | Low | No
FT011 | Product Specification Validation | TC011 | N/A | Verify Product Specifications | User is on the product page | 1. Open product page 2. Scroll to product specifications section 3. Validate all specifications. | Product specifications should be complete and visible (weight, dimensions, material, etc.). | N/A | Fail | QA Name | Ensure no missing details. | Medium | Yes
FT012 | Compare Product Functionality | TC012 | Compare with similar products | Test Product Comparison Feature | User is on the product page | 1. Select product 2. Use the "Compare" feature 3. Add similar products to compare. | Products should be added to the comparison list, and comparison details should be accurate. | N/A | Pass | QA Name | Check for visual bugs in comparison table. | Low | No
FT013 | Wishlist Functionality | TC013 | User Wishlist Data | Verify Add to Wishlist Functionality | User is logged in and on the product page | 1. Open product page 2. Click "Add to Wishlist" 3. Verify product is added to wishlist. | Product should be successfully added to the wishlist, and it should reflect correctly in the wishlist page. | N/A | Pass | QA Name | Test removing items from wishlist. | Medium | Yes
FT014 | Product Delivery Date Estimation | TC014 | Location (Pincode) | Validate Delivery Date Estimation | User is on the product page | 1. Open product page 2. Enter a pincode in the delivery section 3. Check delivery date estimation. | Delivery date should be estimated accurately based on the user's location (pincode). | N/A | Fail | QA Name | Verify delivery date calculation logic. | Medium | Yes
FT015 | Product Return Policy Display | TC015 | N/A | Verify Product Return Policy Display | User is on the product page | 1. Open product page 2. Scroll to return policy section 3. Verify return policy details. | Return policy should be visible and provide clear information regarding the return process. | N/A | Pass | QA Name | Check for missing return policy information. | Medium | Yes
FT016 | Frequently Bought Together | TC016 | N/A | Test "Frequently Bought Together" Feature | User is on the product page | 1. Open product page 2. Review "Frequently Bought Together" section 3. Add suggested products. | Suggested products should be relevant and easily added to the cart via the "Frequently Bought Together" section. | N/A | Pass | QA Name | Test different product combinations. | Low | No
FT017 | Similar Products Suggestions | TC017 | N/A | Verify "Similar Products" Section | User is on the product page | 1. Open product page 2. Review "Similar Products" section. | Relevant products similar to the current one should be displayed for user browsing. | N/A | Pass | QA Name | Verify if suggestions are appropriate. | Medium | No
FT018 | Share Product Functionality | TC018 | Social Media Accounts | Test Share Product Feature | User is on the product page | 1. Open product page 2. Click "Share" button 3. Select a social platform and verify sharing. | Product page link should be shared successfully on the selected social media platform. | N/A | Pass | QA Name | Test sharing on multiple platforms. | Low | No
FT019 | Delivery Charges Calculation | TC019 | Pincode, Delivery Options | Verify Delivery Charges Calculation | User is on the product page | 1. Open product page 2. Enter a pincode in the delivery section 3. Check delivery charges. | Delivery charges should be calculated and displayed based on the user's pincode and selected delivery option. | N/A | Pass | QA Name | Validate various delivery speeds. | Medium | Yes
FT020 | Product Ratings Summary | TC020 | N/A | Verify Ratings Summary | User is on the product page | 1. Open product page 2. Scroll to the product rating summary section 3. Verify rating breakdown. | The rating summary should display the average rating and the distribution of ratings (5-star to 1-star). | N/A | Pass | QA Name | Ensure data matches customer reviews. | Medium | Yes
FT021 | Questions & Answers Section | TC021 | User-Submitted Questions | Validate Questions & Answers Section | User is on the product page | 1. Open product page 2. Scroll to the Questions & Answers section 3. Check for user-submitted Q&As. | Questions and answers should load properly and allow users to submit new questions or answers. | N/A | Pass | QA Name | Test response time for new submissions. | Low | No
FT022 | Similar Product Price Comparison | TC022 | Similar Products | Verify Similar Product Price Comparison | User is on the product page | 1. Open product page 2. Scroll to "Similar Products" section 3. Compare prices of similar products. | The displayed prices for similar products should be accurate and up-to-date. | N/A | Pass | QA Name | Validate currency symbols for prices. | Medium | Yes
FT023 | Promotional Offers Section | TC023 | Coupon Codes, Offers | Validate Promotional Offers Display | User is on the product page | 1. Open product page 2. Scroll to promotional offers section 3. Validate applicable offers. | Offers and promotional discounts should be visible and should apply correctly when selected. | N/A | Pass | QA Name | Test multiple promo codes if possible. | High | No
FT024 | Product Warranty Information | TC024 | Warranty Details | Verify Product Warranty Information Display | User is on the product page | 1. Open product page 2. Scroll to warranty section 3. Validate warranty information. | Product warranty details should be clearly visible and accurate. | N/A | Pass | QA Name | Ensure all variants have correct info. | Low | Yes
FT025 | Scroll Performance | TC025 | N/A | Verify Smooth Scrolling on Product Page | User is on the product page | 1. Open product page 2. Scroll through the page sections 3. Check for any lag or performance issues. | Scrolling should be smooth with no lag or stuttering, even when loading images and reviews. | N/A | Fail | QA Name | Check performance across devices. | Medium | No
FT026 | Breadcrumb Navigation | TC026 | N/A | Validate Breadcrumb Navigation | User is on the product page | 1. Open product page 2. Verify the breadcrumb links 3. Click through different levels of navigation. | Breadcrumb navigation should correctly link to the corresponding category or product pages. | N/A | Pass | QA Name | Ensure consistency across products. | Low | Yes
FT027 | Delivery Option Availability | TC027 | Delivery Options, Pincode | Validate Delivery Option Availability Based on Pincode | User is on the product page | 1. Open product page 2. Enter a pincode 3. Check available delivery options (standard, express, etc.). | Available delivery options should be displayed correctly based on the pincode. | N/A | Pass | QA Name | Test various pincode scenarios. | Medium | Yes
FT028 | Tab Navigation (Details/Reviews) | TC028 | N/A | Validate Tab Navigation (Details, Reviews) | User is on the product page | 1. Open product page 2. Switch between the different tabs (e.g., Product Details, Reviews) | Tab navigation should work smoothly, and the selected content should load without delay. | N/A | Pass | QA Name | Test switching between multiple tabs. | Medium | Yes
FT029 | Video Review Display | TC029 | Video Review | Verify Display and Playability of Video Reviews | User is on the product page | 1. Open product page 2. Scroll to video review section 3. Play a video review. | Video review should play smoothly without buffering, and the display should be responsive. | N/A | Pass | QA Name | Test videos of various lengths. | Medium | No
FT030 | Buy Now Functionality | TC030 | Product Variants | Validate Buy Now Button | User is on the product page | 1. Open product page 2. Select a variant and click "Buy Now" button. | User should be directed to the checkout page with the correct product and variant added. | N/A | Pass | QA Name | Verify cart update after "Buy Now." | High | Yes
UI001 | Font Size and Consistency | TC032 | Product Name, Description | Verify Font Size and Consistency | User is on the product page | 1. Open product page 2. Check fonts for product title, description, price, and buttons. | Fonts should be consistent in style and size, and text should be easily readable. | N/A | Pass/Fail | QA Name | Test across mobile and web. | Medium | Yes
UI002 | Image Zoom Functionality | TC033 | Product Images | Validate Image Zoom Functionality | User is on the product page | 1. Open product page 2. Hover over product images 3. Verify zoom-in function. | Image should zoom in clearly without any distortion. | N/A | Pass/Fail | QA Name | Test multiple images for zoom. | High | Yes
UI003 | Button Placement | TC034 | N/A | Verify Button Placement | User is on the product page | 1. Open product page 2. Verify that "Add to Cart," "Buy Now," and other buttons are correctly placed. | Buttons should be aligned correctly and easily accessible for user interaction. | N/A | Pass/Fail | QA Name | Test for alignment issues. | Medium | Yes
UI004 | Product Image Quality | TC035 | Product Images | Validate Product Image Quality | User is on the product page | 1. Open product page 2. Check product image resolution and clarity. | Product images should be high-resolution, clear, and match the actual product. | N/A | Pass/Fail | QA Name | Test across image formats. | High | Yes
ET001 | Navigation through Product Tabs | TC036 | N/A | Explore Product Tabs Navigation | User is on the product page | 1. Open product page 2. Navigate through tabs (e.g., Overview, Details, Reviews). | All tabs should load smoothly, with content dynamically displayed. | N/A | Pass/Fail | QA Name | Explore different tab orders. | Medium | No
ET002 | Explore Invalid URL Handling | TC037 | Invalid URL | Explore Handling of Invalid Product URL | N/A | 1. Manually alter the URL 2. Access the product page with an invalid product ID. | The system should display an appropriate error message (e.g., "Product not found"). | N/A | Pass/Fail | QA Name | Test different invalid URLs. | Medium | No
RT001 | Product Price Change Impact | TC038 | Updated Product Price | Validate Price Change Impact | User is on the product page | 1. Open product page 2. Update the product price in the database 3. Refresh product page. | The updated price should reflect instantly on the product page. | N/A | Pass/Fail | QA Name | Test for previous versions. | High | Yes
RT002 | Product Details Modification | TC039 | Updated Product Description | Validate Description Change Impact | User is on the product page | 1. Open product page 2. Update the product description 3. Refresh product page. | The updated description should reflect instantly on the product page. | N/A | Pass/Fail | QA Name | Test updates for all products. | Medium | Yes
API001 | Retrieve Product Details API | TC040 | Product ID | Validate Product Details API | Product page exists | 1. Use the Product ID to make an API request 2. Validate the returned product details. | Product details (name, price, description, etc.) should be returned correctly by the API. | N/A | Pass/Fail | QA Name | Test various response codes. | High | Yes
API002 | Retrieve Product Reviews API | TC041 | Product ID | Validate Product Reviews API | Product page exists | 1. Use the Product ID to make an API request 2. Validate the returned reviews data. | Product reviews data should be returned correctly, including user names, ratings, and review text. | N/A | Pass/Fail | QA Name | Test large datasets. | Medium | Yes
PT001 | Page Load under Heavy Traffic | TC042 | Simulate 1000 users | Validate Page Load Performance | User is on the product page | 1. Simulate 1000 users accessing the product page concurrently 2. Measure page load time. | Page should load within acceptable limits (e.g., <3 seconds) even under heavy traffic. | N/A | Pass/Fail | QA Name | Validate across devices. | High | No
PT002 | Image Load Performance | TC043 | Large Product Images | Validate Large Image Load Performance | User is on the product page | 1. Open product page with large product images 2. Measure the time taken for all images to load. | Images should load within 1-2 seconds without impacting page performance. | N/A | Pass/Fail | QA Name | Test various image sizes. | Medium | Yes
CB001 | Cross-Browser Compatibility | TC044 | Chrome, Firefox, Safari, Edge | Validate Page Layout Across Browsers | User is on the product page | 1. Open product page in Chrome 2. Repeat in Firefox 3. Repeat in Safari 4. Repeat in Edge | The page layout should be consistent across all tested browsers. | N/A | Pass/Fail | QA Name | Test different versions of each browser. | High | Yes
CB002 | Cross-Browser Compatibility | TC045 | Various Browsers | Verify Functional Elements in Different Browsers | User is on the product page | 1. Open product page in Chrome 2. Interact with key elements (buttons, links) 3. Repeat in other browsers. | Key elements (buttons, links) should be functional across all tested browsers. | N/A | Pass/Fail | QA Name | Ensure that elements are interactive. | High | Yes
CB003 | Cross-Browser Compatibility | TC046 | Different Screen Sizes | Test Responsive Design Across Browsers | User is on the product page | 1. Open product page in Chrome on different screen sizes (desktop, tablet, mobile) 2. Repeat for other browsers. | The product page should be responsive and display correctly on various screen sizes across all browsers. | N/A | Pass/Fail | QA Name | Test on various resolutions. | Medium | Yes
CB004 | Cross-Browser Compatibility | TC047 | Browser Dev Tools | Validate CSS and JavaScript Performance | User is on the product page | 1. Open product page in Chrome 2. Use Developer Tools to check CSS and JavaScript performance 3. Repeat for other browsers. | CSS and JavaScript should perform optimally without errors across all tested browsers. | N/A | Pass/Fail | QA Name | Monitor for performance issues. | Medium | No
CB005 | Cross-Browser Compatibility | TC048 | Various Browsers | Check for Browser-Specific Bugs | User is on the product page | 1. Open product page in Chrome 2. Report any browser-specific bugs 3. Repeat for other browsers. | The product page should be free of browser-specific bugs across all tested browsers. | N/A | Pass/Fail | QA Name | Document any browser-specific issues. | High | No